## Sheet1
Fatima Jinnah Women University
Silver Jubilee Celebrations 1998-2023
Proposed Implementation Plan (December 2022- June 2023 )
The mission of the 25th-anniversary committee is to engage the entire FJWU community, including faculty, alumni, administration, staff, and students, in the yearlong celebrations of the 25th anniversary of the founding of Fatima Jinnah Women University. The main goal of the 25th-anniversary celebration and commemoration is to highlight the achievements of the institutional community to celebrate the growth and the success of FJWU and bring the FJWU community together in a series of events beginning December 2022 and culminating on 28th december, 2023. These events will be a combination of academic activities, alumni gatherings, performances, exhibitions and student’s celebrations
December 2022- June 2023
Sr.no | Activities | December, 2022 | January, 2023 | February, 2023 | March, 2023 | April, 2023 | May , 2023 | June , 2023 | July, 2023 | August, 2023 | September, 2023 | October, 2023 | November , 2023 | December , 2023
1 | Academic& Research Activities | Silver Jubilee Tag Souvenirs FJWU silver jubilee logo design for publicity of events throughout the year. | FJWU Convocation | Faces for 25 Campus-wide exhibition and photo gallery highlighting who has made a significant contribution to the University over the years. | Trailer /teaser of the Event trailer/ teaser of the Event by adding of name & date of the Event, catchy copywriting, event statistics, programs, etc. The primary purpose of this trailer is to attract an audience by highlighting the exciting and noteworthy parts. | Career Expo This recruiting event allows students and employers to meet, establish professional relationships, and discuss potential job and internship opportunities. | Journaling Session This will allow students to express themselves, learn from their mistakes, and appreciate the things that make them happy. | Student Success Stories One Day Event on Students success stories based on how well Fatminians are prepared to accomplish their current and future academic, personal and professional goals through the development, knowledge and sense of responsibility. | Workshop on Enhancing Employability and Financial Literacy | Sustainability initiatives “FJWU fostering future”: Plantation drives Recycling drives Gardening club | Prominent Research by Faculty faculty-wise colloquium to highlight the prominent researches. All departments will coordinate with their respective faculties. | Best Department Research and Innovation Event | Commemorative digest showcasing 25 years celebrations and the work of winners in various competitions during the year. | Three Days Event – Student Achievement (Graduate Research Conference) All Departments will participate in the Cross Disciplinary Graduate Research Conference at FJWU (Bachelors, Masters, MPhil, and Doctoral) to showcase their scholarly work and promise as future innovators, researchers, and academics.
|  | FJWU Video short (3-4 minutes) FJWU Video which will be showcased on 28th December, 2022 Annual Dinner. Release of FJWU Song on Annual Dinner |  | Event on Theme "When everything changed Painting competition (open to all) highlighting the COVID-19 pandemic. | Seminar on Women Empowerment and Role of FJWU All academic departments will arrange a seminar on Women Empowerment and the Role of FJWU. Women's role in every segment of society is vital, and society's development is linked with women's empowerment within that environment. Each department will invite their outstanding alumni for the seminar and would highlight how their life at FJWU contributed towards their success. | Colloquium on International Collaboration of FJWU so far colloquium highlighting International Collaborations as International academic collaboration plays an essential role in the creation of educational models and help the educational system to act effectively. |  |  |  |  | Faculty Award Award Ceremony recognizing faculty of the year award in terms of research & teaching.
|  | Alumni Awards Award Ceremony recognizing outstanding academic or non-academic achievements of Graduates of FJWU. The award ceremony will further help in actively involving alumni in the activities of the university. |  | Recognition of FJWU Vice Chancellors over the years and their significant contributions | Women's Week - Interdepartmental Competitions (3 days event along with entrepreneurship fair) |  |  |  |  | Sports Competition |  | E-Games Tournament E-Game Tournament by arranging competitions using video games.
Launch of University Oral History Project (recorded audio-visual histories from 17 significant people in the University's past)
|  | Entrepreneurial Fair along with twin cities Interuniversity competitions | Convocation Gala Festival |  |  |  | Entreprenurship Fair | [6 empty] | Inter-University competitions along with grand entrepreneurial gala